## README
UniConnect — Student Portal Consolidation — Project data workbook
BISY2004 Assessment 2 ¦ Group XX ¦ Scenario C ¦ Fictional organisation: Southern Coast University (SCU) — fictional ¦ Status date: Fri 25 Sep 2026
Everything comes from one data file (data/project.yaml), so the WBS IDs are the same in ProjectLibre, Trello, this workbook and the diagrams. Numbers you type in are inputs; everything else is a formula.
Sheet | Purpose
Resources | Role rates (AUD/hour) and headcount — input to all labour costs
Assignments | Task × role × units → hours × rate = labour cost (formulas)
Schedule_WBS | WBS work packages with ProjectLibre IDs, baseline/forecast dates, float, cost, % complete, PV/EV/AC
Risk_Register | 13 risks, 5×5 scoring (Score = L×I), rating bands, residual risk, EMV → contingency reserve
Risk_Heatmap_5x5 | Inherent and residual heat maps (COUNTIFS) with risk IDs in each cell
Cost_Baseline | Cost by WBS branch, BAC, contingency + management reserve, total budget, monthly time-phased PV
EVM_Status | Weekly PV/EV/AC to the status date; SV, CV, SPI, CPI, EAC (3 methods), ETC, VAC, TCPI with RAG
Dashboard | KPI tiles, S-curve, risks by rating, milestone status, quality status
Stakeholder_Register | Power/interest scores, quadrant formula, reason, attitude current→desired, strategy
Comms_Plan | Who gets what, how, how often, owner, feedback loop
RACI | Deliverables × roles with an 'exactly one A' check per row
Quality_Metrics | Metrics, targets, current values, RAG
Control_Chart | Defects per week with mean, UCL = mean + 3σ, LCL = max(0, mean − 3σ)
Change_Log | CR-01..03 with scope/schedule/cost/risk impact and CCB decision
Issue_Log | ISS-01..05 linked to risks, WBS, owners and actions
Traceability | WBS → ProjectLibre ID → Trello card → cost → risks → RACI accountable → quality metric
Closure | Closure checklist, benefits realisation plan, lessons learned
Lookups | Validation lists and the 5×5 scoring scales
How to read the status words
Green | on target (SPI/CPI 0.95 or more)
Amber | keep an eye on it (0.90 to 0.95)
Red | needs action now (under 0.90)
Note | No colours are used, so every rating is written as a word in the cell.

## Dashboard
UniConnect — Project status dashboard (status date 25 Sep 2026)
Every tile is a formula that pulls from EVM_Status, Risk_Register, Issue_Log, Change_Log and Quality_Metrics.
SPI |  |  |  | CPI |  |  | % complete |  | EAC
0.91363 |  |  |  | 0.95728 |  |  | 24.64% |  | 940353.926
VAC |  |  |  | Open High risks |  |  | Open issues |  | CRs approved
-40173.926 |  |  |  | 7 |  |  | 3 |  | 2 of 3
Overall RAG | AMBER |  | Forecast go-live 04/02/2027 vs hard deadline 05/02/2027 — buffer 1 working day(s) before CR-02 recovery
Milestones | [6 empty] | Quality metrics
ID | Milestone |  | Baseline | Forecast | Slip (d) | Status | ID | Metric | Current | RAG
M1 | Charter approved |  | 2026-07-17 | 2026-07-17 | 0 | Achieved | Q01 | Migration record accuracy | 95.3% (trial 1) | Red
M2 | Design sign-off |  | 2026-09-04 | 2026-09-04 | 0 | Achieved | Q02 | Portal availability | 99.2% (test env.) | Amber
M3 | Build complete |  | 2026-10-26 | 2026-10-26 | 0 | On track | Q03 | Page load p95 at 5,000 concurrent users | Not yet tested | Grey
M4 | Trial migration passed |  | 2026-11-02 | 2026-11-16 | 10 | At risk | Q04 | WCAG 2.1 AA critical failures | 2 (Sprint 1 scan) | Amber
M5 | UAT sign-off |  | 2026-12-14 | 2027-01-06 | 10 | At risk | Q05 | UAT pass rate | Not started | Grey
M6 | Go-live |  | 2027-01-20 | 2027-02-04 | 10 | At risk | Q06 | Open Severity-1 defects at go-live | 1 open (ISS-02) | Amber
M7 | Project closed |  | 2027-03-11 | 2027-03-25 | 10 | At risk | Q07 | Portal-related helpdesk tickets | Baseline 4,200/month | Grey
Risks by rating
Rating | Inherent | Residual
Extreme | 0 | 0
High | 7 | 1
Medium | 6 | 7
Low | 0 | 5
Formulas:
Slip (d) = IF([CPI]<=[Baseline],0,NETWORKDAYS([Baseline],[CPI],Holidays)-1)

## Risk_Register
Risk register (5×5)
Score = L × I; bands Low 1–4, Medium 5–9, High 10–16, Extreme 20–25; EMV = probability × cost impact
ID | Type | Category | Description (cause → event → effect) | WBS links | L | I | Score | Rating | Owner | Strategy | Response | Trigger | Res. L | Res. I | Res. score | Res. rating | Probability | Cost impact | EMV | Status | Heat key | Res. key
R01 | threat | Data | Because legacy SIS/portal data has duplicate and inconsistent student records (cause), trial migration may fail reconciliation (event), delaying the critical migration path and go-live (effect). | 4.1, 4.2, 4.3 | 4 | 4 | 16 | High | Data Engineer | Mitigate | Early data profiling in 2.1; de-duplication rules in 4.1; reconciliation scripts; contingency: cleansing mini-sprint + contractor. | > 1% duplicate/unmatched records in trial migration 1 | 2 | 3 | 6 | Medium | 65% | 60000 | 39000 | Materialised → ISS-01 | 4-4 | 2-3
R02 | threat | Technical/Vendor | Because the LMS vendor's SSO/API support is immature (cause), SSO or LMS integration may not work (event), delaying Sprint 1 and integration APIs (effect). | 2.3, 3.1, 3.5 | 3 | 4 | 12 | High | Solution Architect | Mitigate | SSO proof of concept in Sprint 1; vendor SLA with escalation; weekly vendor call (C07). | SSO PoC fails token exchange by end of Sprint 1 | 2 | 3 | 6 | Medium | 40% | 15000 | 6000 | Open — partly occurred (ISS-02) | 3-4 | 2-3
R03 | threat | Compliance/Privacy | Because migration copies identifiable student data between environments (cause), personal information could be exposed (event), causing a notifiable data breach under APP 11 (effect). | 2.4, 4.2, 4.3, 4.4 | 2 | 5 | 10 | High | Privacy Officer | Mitigate | PIA; masked data in non-production; encrypted transfer; access logging; MFA for all users (CR-03). | Any unmasked personal data found in a non-production environment | 1 | 5 | 5 | Medium | 15% | 40000 | 6000 | Open | 2-5 | 1-5
R04 | threat | Schedule | Because go-live is close to Semester 1 enrolment (cause), cutover could clash with the enrolment peak (event), disrupting enrolments (effect). | 4.4, 6.3 | 3 | 4 | 12 | High | Project Manager | Avoid | Fixed cutover window 14–20 Jan 2027, change freeze from 1 Feb; fallback: go-live in mid-semester break with legacy portals kept live. | Forecast go-live later than 29 Jan 2027 | 1 | 4 | 4 | Low | 40% | 15000 | 6000 | Open — watch (forecast go-live 4 Feb vs 5 Feb deadline) | 3-4 | 1-4
R05 | threat | Resource | Because developers are in high demand (cause), a key developer may resign (event), slowing sprints (effect). | 3.1, 3.2, 3.3, 3.4 | 2 | 3 | 6 | Medium | Development Lead | Mitigate | Pair programming, documented code, retention bonus at go-live. | Resignation notice from a developer | 2 | 2 | 4 | Low | 15% | 15000 | 2250 | Open | 2-3 | 2-2
R06 | threat | Scope | Because faculties want their own features (cause), unapproved scope may enter sprints (event), consuming float and budget (effect). | 2.2, 3.2, 3.3, 3.4 | 4 | 3 | 12 | High | Project Manager | Mitigate | MoSCoW backlog; all requests through CCB (C05); Phase 2 backlog. | > 2 new feature requests in a sprint | 2 | 3 | 6 | Medium | 65% | 10000 | 6500 | Occurred → CR-01 deferred | 4-3 | 2-3
R07 | threat | Technical/Performance | Because 5,000+ students log in at once during enrolment (cause), the portal could slow or fail (event), stopping enrolments (effect). | 5.4, 6.3 | 3 | 5 | 15 | High | Solution Architect | Mitigate | Load test at 5,000 concurrent users; autoscaling; CDN caching. | p95 page load > 2 s in load test | 2 | 4 | 8 | Medium | 40% | 15000 | 6000 | Open | 3-5 | 2-4
R08 | threat | Compliance/Accessibility | Because legacy templates are not accessible (cause), the portal may fail WCAG 2.1 AA (event), excluding students with disability (effect). | 2.5, 5.3 | 3 | 3 | 9 | Medium | UX Designer | Mitigate | Accessible design system; automated scans each sprint; audit 5.3. | Any critical failure in a sprint accessibility scan | 1 | 3 | 3 | Low | 40% | 10000 | 4000 | Open — ISS-04 | 3-3 | 1-3
R09 | threat | Organisational | Because students are used to the old portals (cause), adoption may be low (event), reducing benefits (effect). | 6.1, 6.2 | 3 | 3 | 9 | Medium | Change & Training Lead | Mitigate | SRC co-design; pilot champions; go-live campaign (C04, C08). | Pilot satisfaction < 70% | 2 | 2 | 4 | Low | 40% | 8000 | 3200 | Open | 3-3 | 2-2
R10 | threat | Financial | Because licences are priced in USD (cause), a weaker AUD could raise licence costs (event), exceeding the cost baseline (effect). | 6.3 | 3 | 3 | 9 | Medium | Finance Office | Transfer | Fixed-AUD pricing clause negotiated with the vendor. | AUD/USD < 0.62 before contract signature | 1 | 3 | 3 | Low | 40% | 10000 | 4000 | Open — fixed-AUD clause in negotiation | 3-3 | 1-3
R11 | threat | Operational | Because all students switch at once (cause), the Service Desk may be overwhelmed (event), causing long waits and complaints (effect). | 6.1, 6.4 | 4 | 3 | 12 | High | Change & Training Lead | Mitigate | FAQs, chatbot, surge staff roster, daily hypercare stand-up (C09). | > 300 portal tickets/day during hypercare | 2 | 3 | 6 | Medium | 65% | 8000 | 5200 | Open | 4-3 | 2-3
R12 | opportunity | Opportunity | Because SCU already runs an identity platform (cause), SSO could reuse it (event), avoiding a separate identity licence and speeding Sprint 1 (effect). | 2.3, 3.1 | 3 | 3 | 9 | Medium | Solution Architect | Exploit | Design SSO on the existing platform; cancel separate IdP quote. | Architecture review confirms compatibility | 5 | 3 | 15 | High | 40% | -30000 | -12000 | Realised in 2.3 (saving not netted from reserve) | 3-3 | 5-3
R13 | threat | Schedule | Because of the university shutdown and staff leave over summer (cause), key people may be unavailable (event), slowing the faculty pilot (effect). | 6.2 | 4 | 2 | 8 | Medium | Project Manager | Accept | Accepted: shutdown modelled in the ProjectLibre calendar; leave plan agreed by Oct. | Leave requests overlapping 6.2 | 4 | 2 | 8 | Medium | 65% | 4000 | 2600 | Accepted | 4-2 | 4-2
[12 empty] | Contingency reserve (threat EMV) | [6 empty] | 90750
[12 empty] | Opportunity EMV (not netted) | [6 empty] | -12000
[12 empty] | High/Extreme risks open | [6 empty] | 7

## Risk_Heatmap_5x5
5×5 risk heat map (inherent and residual)
Each cell counts the risks at that likelihood and impact (COUNTIFS), then shows the band and the risk IDs. Bands: 1–4 Low, 5–9 Medium, 10–16 High, 20–25 Extreme.
Inherent risk (before response) | [5 empty] | Residual risk (after response)
Likelihood ↓ / Impact → | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe | Likelihood ↓ / Impact → | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe
5 Almost certain | [5 empty] | 5 Almost certain |  |  | 1 · High R12
4 Likely |  | 1 · Medium R13 | 2 · High R06 R11 | 1 · High R01 |  | 4 Likely |  | 1 · Medium R13
3 Possible |  |  | 4 · Medium R08 R09 R10 R12 | 2 · High R02 R04 | 1 · High R07 | 3 Possible
2 Unlikely |  |  | 1 · Medium R05 |  | 1 · High R03 | 2 Unlikely |  | 2 · Low R05 R09 | 4 · Medium R01 R02 R06 R11 | 1 · Medium R07
1 Rare | [5 empty] | 1 Rare |  |  | 2 · Low R08 R10 | 1 · Low R04 | 1 · Medium R03
Risks plotted | 13 |  |  |  |  | Risks plotted | 13
Check: heat-map count equals register count | OK
What it shows: seven threats start as High (R01 at 4×4 is the worst one). After our responses none of them is above Medium. R03 stays Medium (1×5) because a data breach would still be really bad. R12 is an opportunity, so we want it to happen: its residual score (5×3) being high is a good thing.

## Cost_Baseline
Cost baseline, reserves and budget (AUD)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
WBS | Level-1 deliverable | Labour hours | Labour cost | Fixed / material | Subtotal | % of BAC | Month | Planned value (month) | Cumulative PV | % of BAC
1 | Project Management | 1120 | 125520 | 0 | 125520 | 13.94% | Jul 2026 | 42500 | 42500 | 4.721%
2 | Requirements & Design | 700 | 76900 | 0 | 76900 | 8.543% | Aug 2026 | 72960 | 115460 | 12.83%
3 | Portal Build (Agile) | 1500 | 150800 | 0 | 150800 | 16.75% | Sep 2026 | 143480 | 258940 | 28.77%
4 | Data Migration | 740 | 76400 | 0 | 76400 | 8.487% | Oct 2026 | 136190 | 395130 | 43.89%
5 | Testing & Quality | 1140 | 115160 | 25000 | 140160 | 15.57% | Nov 2026 | 113120 | 508250 | 56.46%
6 | Deployment & Transition | 1040 | 106400 | 224000 | 330400 | 36.7% | Dec 2026 | 56610 | 564860 | 62.75%
[7 empty] | Jan 2027 | 275250 | 840110 | 93.33%
| Cost baseline (BAC) | 6240 | 651180 | 249000 | 900180 | 100% | Feb 2027 | 49370 | 889480 | 98.81%
| Contingency reserve (Σ threat EMV, Risk_Register) |  |  |  | 90750 | 10.08% | Mar 2027 | 10700 | 900180 | 100%
| Performance measurement baseline = BAC + contingency |  |  |  | 990930 |  | Monthly PV is time-phased from the ProjectLibre baseline (flat work contour).
| Management reserve (5% of BAC, sponsor-held) |  |  |  | 45009 | 5%
| Total project budget |  |  |  | 1035939
| Check: BAC equals Schedule_WBS total |  |  |  | OK

## EVM_Status
Earned value status (to 25 Sep 2026)
Weekly cumulative PV/EV/AC from the ProjectLibre baseline and progress; summary uses the Schedule_WBS task totals
Status-date summary
Week | Week ending | PV (cum) | EV (cum) | AC (cum) | SV | CV | SPI | CPI | Budget at completion (BAC) | 900180 |  | Cost baseline (Schedule_WBS)
1 | 2026-07-10 | 6700 | 6700 | 6700 | 0 | 0 | 1 | 1 | Planned value (PV / BCWS) | 242800 |  | ProjectLibre BCWS at status date
2 | 2026-07-17 | 13400 | 13400 | 13400 | 0 | 0 | 1 | 1 | Earned value (EV / BCWP) | 221830 |  | % complete × baseline cost
3 | 2026-07-24 | 28900 | 28900 | 28900 | 0 | 0 | 1 | 1 | Actual cost (AC / ACWP) | 231730 |  | ProjectLibre actual cost
4 | 2026-07-31 | 42500 | 42500 | 42500 | 0 | 0 | 1 | 1 | Schedule variance SV = EV − PV | -20970 |  | Negative = behind schedule
5 | 2026-08-07 | 53650 | 53650 | 53650 | 0 | 0 | 1 | 1 | Cost variance CV = EV − AC | -9900 |  | Negative = over budget
6 | 2026-08-14 | 64800 | 64800 | 64800 | 0 | 0 | 1 | 1 | SPI = EV / PV | 0.91363 | Amber | < 1 behind schedule
7 | 2026-08-21 | 83350 | 83350 | 85210 | 0 | -1860 | 1 | 0.97817 | CPI = EV / AC | 0.95728 | Green | < 1 over budget
8 | 2026-08-28 | 107000 | 107000 | 110720 | 0 | -3720 | 1 | 0.9664 | EAC (typical) = BAC / CPI | 940353.926 |  | Current cost efficiency continues
9 | 2026-09-04 | 149300 | 147200 | 152180 | -2100 | -4980 | 0.98593 | 0.96728 | EAC (atypical) = AC + (BAC − EV) | 910080 |  | Variance treated as one-off
10 | 2026-09-11 | 180600 | 176400 | 182640 | -4200 | -6240 | 0.97674 | 0.96583 | EAC (CPI × SPI) = AC + (BAC − EV)/(CPI×SPI) | 1007341.4557 |  | Schedule pressure also drives cost
11 | 2026-09-18 | 211700 | 199115 | 207185 | -12585 | -8070 | 0.94055 | 0.96105 | ETC = EAC − AC | 708623.926 |  | Cost to finish (typical)
12 | 2026-09-25 | 242800 | 221830 | 231730 | -20970 | -9900 | 0.91363 | 0.95728 | VAC = BAC − EAC | -40173.926 |  | Forecast overrun (typical)
13 | 2026-10-02 | 269700 | [6 empty] | TCPI = (BAC − EV)/(BAC − AC) | 1.0148 |  | > 1 = must work more efficiently
14 | 2026-10-09 | 293660 | [6 empty] | % complete (EV / BAC) | 24.64% |  | Physical progress
15 | 2026-10-16 | 321370 | [6 empty] | % planned (PV / BAC) | 26.97% |  | Where we should be
16 | 2026-10-23 | 352920 | [6 empty] | Contingency reserve | 90750 |  | Covers VAC?
17 | 2026-10-30 | 395130 | [6 empty] | EAC within BAC + contingency? | Yes |  | Funding test for the recommendation
18 | 2026-11-06 | 437130
19 | 2026-11-13 | 465600
20 | 2026-11-20 | 490850 | [6 empty] | RAG thresholds: ≥ 0.95 Green · 0.90–0.95 Amber · < 0.90 Red (agreed with sponsor).
21 | 2026-11-27 | 505780 | [6 empty] | Check: weekly status row equals task totals | OK
22 | 2026-12-04 | 526210
23 | 2026-12-11 | 546640
24 | 2026-12-18 | 558110
25 | 2026-12-25 | 564860
26 | 2027-01-01 | 564860
27 | 2027-01-08 | 576510
28 | 2027-01-15 | 679040
29 | 2027-01-22 | 827910
30 | 2027-01-29 | 840110
31 | 2027-02-05 | 855360
32 | 2027-02-12 | 870610
33 | 2027-02-19 | 884480
34 | 2027-02-26 | 889480
35 | 2027-03-05 | 894820
36 | 2027-03-12 | 900180

## Stakeholder_Register
Stakeholder register & power–interest classification
Quadrant formula: power ≥ 4 and interest ≥ 4 → Manage closely; power ≥ 4 → Keep satisfied; interest ≥ 4 → Keep informed; else Monitor
ID | Stakeholder | Role | Power (1–5) | Interest (1–5) | Quadrant (formula) | Reason for classification | Current attitude | Desired attitude | Engagement strategy | Comms ref
S01 | Deputy Vice-Chancellor (Education) | Project sponsor | 5 | 5 | Manage closely | Funds the project, chairs the steering committee and owns the go/no-go decision. | Supportive | Leading | Fortnightly steering committee; early warning of variances; decisions requested with options. | C01, C05
S02 | Chief Information Officer | IT executive | 5 | 4 | Manage closely | Owns IT architecture, operations and the identity platform; can reprioritise IT staff. | Supportive | Leading | Steering committee member; architecture decisions escalated directly. | C01, C02
S03 | Academic Registrar | Data owner — student records | 4 | 5 | Manage closely | Owns enrolment and student data; signs migration reconciliation; worried about enrolment disruption. | Neutral | Supportive | Involve in cleansing decisions and reconciliation sign-off; privacy briefings before each migration. | C01, C06
S04 | Faculty Deans | Academic leadership | 4 | 3 | Keep satisfied | Can escalate to the DVC and control faculty staff time, but day-to-day interest is moderate. | Resistant | Neutral | Monthly faculty briefings; route feature requests through the CCB (CR-01). | C11, C02
S05 | Students (domestic & international) | Primary users | 2 | 5 | Keep informed | Most affected by the change but have no formal decision rights; influence is via the SRC. | Unaware | Supportive | Co-design via SRC, pilot, newsletters and go-live campaign; multilingual guides for international students. | C04, C08
S06 | Student Representative Council (SRC) | Student voice | 3 | 4 | Keep informed | Speaks for students and can create reputational pressure, but has no budget or approval authority. | Neutral | Supportive | Sprint review participation; co-design sessions; pilot champions. | C03, C04
S07 | Academic staff | Secondary users (LMS gateway) | 2 | 3 | Monitor | Affected only via LMS links and student questions; little authority over the project. | Unaware | Neutral | General updates through faculty briefings; quick-reference guide. | C11
S08 | IT Service Desk | Support provider | 2 | 4 | Keep informed | Absorbs go-live ticket volume (R11) but does not approve scope or budget. | Concerned | Supportive | Early training, knowledge base, hypercare stand-ups. | C08, C09
S09 | Finance Office | Budget & fees integration | 4 | 3 | Keep satisfied | Releases funds and owns the fees system, but is interested mainly in cost and integration points. | Neutral | Supportive | Monthly cost/EVM summary; CCB member for cost-affecting changes. | C01, C05
S10 | Privacy Officer | Compliance (Privacy Act/APPs) | 4 | 4 | Manage closely | Can halt migration on privacy grounds and must approve the PIA (R03, CR-03). | Cautious | Supportive | PIA co-owner; privacy briefing before every migration; CCB member. | C06, C05
S11 | Accessibility Services | Disability advocacy | 2 | 4 | Keep informed | Advocates for students with disability (WCAG, R08) but has advisory, not approval, power. | Neutral | Supportive | Prototype testing and WCAG audit review; sprint reviews. | C03
S12 | LMS vendor | Supplier — LMS API | 4 | 2 | Keep satisfied | Controls the LMS API and SSO support (R02) through the contract, but has low interest in our timeline. | Neutral | Supportive | Weekly vendor call; SLA escalation path via the CIO. | C07
S13 | Portal platform vendor | Supplier — portal platform | 3 | 4 | Keep informed | Keen on a reference site; limited leverage because the contract is signed. | Supportive | Supportive | Weekly vendor call; joint defect triage. | C07
S14 | TEQSA (regulator) | External regulator | 5 | 1 | Keep satisfied | Can impose conditions on the university but is only interested if student outcomes or data are compromised. | Unaware | Neutral | Keep satisfied via the Registrar's routine compliance reporting; notify only if a material incident occurs. | C10
| Manage closely | 4
| Keep satisfied | 4
| Keep informed | 5
| Monitor | 1

## Comms_Plan
Communication plan
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
ID | Audience | Information | Method | Frequency | Owner | Feedback | Stakeholders served
C01 | Steering committee (DVC, CIO, Registrar, Finance) | Status dashboard, EVM, top risks, decisions needed | Meeting + dashboard PDF | Fortnightly | Project Manager | Minutes and action log | S01, S02, S03, S09
C02 | Sponsor, CIO, Deans, Privacy Officer | Weekly status report (RAG, SPI/CPI, issues) | Email report | Weekly (Friday) | Project Manager | Reply/queries to PM | S02, S04
C03 | Registrar's team, SRC, Accessibility Services | Sprint demo of working features | Sprint review (hybrid meeting) | Every 2 weeks | Development Lead | Backlog items raised in Trello | S06, S11
C04 | Students | What is changing, when, pilot invitations | Newsletter, portal banner, social media | Monthly; weekly from Dec | Change & Training Lead | Survey and SRC channel | S05, S06
C05 | Change Control Board | Change requests with impact analysis | CCB meeting | Fortnightly or ad hoc | Project Manager | Decision recorded in change log | S01, S09, S10
C06 | Privacy Officer, Registrar | Migration controls, masking, reconciliation results | Privacy briefing | Before each migration run | Data Engineer | Written approval to proceed | S03, S10
C07 | LMS vendor, portal platform vendor | Integration defects, API changes, SLAs | Vendor call | Weekly | Solution Architect | Joint defect log | S12, S13
C08 | Students, staff, IT Service Desk | Go-live comms pack: how to log in, where to get help | Email, intranet, FAQs, posters | 4 weeks, 1 week and day 0 before go-live | Change & Training Lead | Help-page analytics, tickets | S05, S08
C09 | IT Service Desk, Dev, Data Engineer | Incidents, ticket trends, fixes | Stand-up (15 min) | Daily during hypercare | Project Manager | Incident log | S08
C10 | TEQSA (via Registrar) | Compliance summary; material incidents only | Formal report | Quarterly / as required | Academic Registrar | Regulator correspondence | S14
C11 | Faculty Deans, academic staff | Scope, dates, pilot, LMS link changes | Faculty briefing | Monthly | Project Manager | Q&A; requests routed to CCB | S04, S07

## RACI
RACI matrix
Exactly one A (Accountable) per deliverable — checked by formula
Deliverable | WBS | Sponsor | Project Manager | Business Analyst | Solution Architect | Development Lead | Data Engineer | Test Lead | UX Designer | Change & Training Lead | Privacy Officer | A count | Check
Project charter | 1.1 | A | R | C | I | I | I | I | I | I | C | 1 | OK
PM plan & baselines / monitoring & control | 1.2, 1.3 | I | A | R | C | C | C | C | I | C | I | 1 | OK
Requirements & audit | 2.1, 2.2 | I | C | A | C | C | R | I | R | C | C | 1 | OK
Solution & SSO architecture | 2.3 | I | C | C | A | R | C | I | C | I | C | 1 | OK
Privacy Impact Assessment | 2.4 | I | C | R | C | I | C | I | I | I | A | 1 | OK
UX prototype & accessibility | 2.5, 5.3 | I | I | C | I | C | I | R | A | C | I | 1 | OK
Portal features (Sprints 1–4) & configuration | 3.1, 3.2, 3.3, 3.4, 3.6 | I | C | R | C | A | I | R | R | I | I | 1 | OK
Integration APIs & load testing | 3.5, 5.4 | I | I | C | A | R | C | R | I | I | I | 1 | OK
Data migration (mapping, trials, final) | 4.1, 4.2, 4.3, 4.4 | I | C | R | C | C | A | R | I | I | C | 1 | OK
Testing (SIT, security, UAT, regression) | 5.1, 5.2, 5.5, 5.6 | I | C | R | C | R | C | A | C | C | C | 1 | OK
Training, pilot & go-live cutover | 6.1, 6.2, 6.3 | C | A | C | R | R | R | C | I | R | I | 1 | OK
Hypercare, decommissioning & closure | 6.4, 6.5, 1.4 | C | A | R | R | R | R | C | I | R | C | 1 | OK
R = Responsible · A = Accountable (one per row) · C = Consulted · I = Informed

## Quality_Metrics
Quality metrics
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
ID | Metric | Target | Measurement method | Frequency | Owner | Current value | RAG | WBS
Q01 | Migration record accuracy | ≥ 99.5% reconciled | Automated reconciliation report vs source counts | Each trial run | Data Engineer | 95.3% (trial 1) | Red | 4.3
Q02 | Portal availability | ≥ 99.5% | Uptime monitoring | Monthly | Solution Architect | 99.2% (test env.) | Amber | 6.4
Q03 | Page load p95 at 5,000 concurrent users | < 2 s | Load test tool (5.4) | Load test + go-live | Solution Architect | Not yet tested | Grey | 5.4
Q04 | WCAG 2.1 AA critical failures | 0 | Automated scan each sprint + audit | Each sprint | UX Designer | 2 (Sprint 1 scan) | Amber | 5.3
Q05 | UAT pass rate | ≥ 95% | UAT scripts passed / executed | Daily in UAT | Test Lead | Not started | Grey | 5.5
Q06 | Open Severity-1 defects at go-live | 0 | Defect tracker | Weekly | Test Lead | 1 open (ISS-02) | Amber | 5.6
Q07 | Portal-related helpdesk tickets | −30% within 3 months | Service Desk reports vs 4,200/month baseline | Monthly after go-live | Change & Training Lead | Baseline 4,200/month | Grey | 6.4

## Control_Chart
Control chart — defects logged per week
Mean and σ from the stable baseline period (weeks 3–11); UCL = mean + 3σ; LCL = max(0, mean − 3σ)
Week | Week ending | Defects | Mean | UCL | LCL | Out of control? | Baseline mean | 6
3 | 2026-07-24 | 6 | 6 | 9.6742 | 2.3258 | No | Baseline σ (sample) | 1.2247
4 | 2026-07-31 | 5 | 6 | 9.6742 | 2.3258 | No | UCL | 9.6742
5 | 2026-08-07 | 7 | 6 | 9.6742 | 2.3258 | No | LCL | 2.3258
6 | 2026-08-14 | 4 | 6 | 9.6742 | 2.3258 | No
7 | 2026-08-21 | 6 | 6 | 9.6742 | 2.3258 | No
8 | 2026-08-28 | 5 | 6 | 9.6742 | 2.3258 | No
9 | 2026-09-04 | 8 | 6 | 9.6742 | 2.3258 | No
10 | 2026-09-11 | 6 | 6 | 9.6742 | 2.3258 | No
11 | 2026-09-18 | 7 | 6 | 9.6742 | 2.3258 | No
12 | 2026-09-25 | 14 | 6 | 9.6742 | 2.3258 | YES — investigate
Interpretation: Week 12 (14 defects) is above the UCL: a special cause, traced to duplicate records in trial migration 1 (ISS-01), not random variation. Action: root-cause analysis and CR-02.

## Change_Log
Change log (CCB decisions)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
CR | Date | Requester | Description | WBS affected | Risks / issues | Scope impact | Schedule impact | Cost impact | Risk impact | CCB decision | CCB date | Rationale | Baseline updated | Artefacts updated
CR-01 | 2026-08-26 | Faculty of Business (Dean) | Add mobile push notifications for timetable and fee reminders. | 3.2, 3.6 | R06, ISS-03 | New feature + native app work (out of scope) | +10 working days on Sprint 2/3 (critical-path pressure) | +$42,000 | Raises R06 and R05 | Deferred | 2026-09-02 | Scope creep; would consume float and threaten go-live. Added to Phase 2 backlog. Email notifications (3.6) cover the need. | No | Change log, Phase 2 backlog (Trello), comms to Deans (C11)
CR-02 | 2026-09-24 | Data Engineer / Project Manager | Add a data-cleansing mini-sprint and a 3-week contract data engineer to recover trial migration 1 (response to ISS-01). | 4.2, 4.3 | R01, R04, ISS-01 | No change to product scope; adds cleansing activity | Recovers about 8 of the 10 forecast slip days (crashing 4.2/4.3 + fast-tracking SIT preparation) | +$23,800 (contractor $15,600 + internal effort $8,200) from contingency reserve | Reduces R01 and R04; small new onboarding risk | Approved | 2026-09-25 | Protects the critical path and hard go-live deadline; cost is within the R01 contingency allocation ($39,000). | Yes — cost baseline +$23,800 (contingency drawdown); schedule re-baselined as Baseline 1 from 28 Sep | Change log, cost baseline, ProjectLibre schedule, risk register (R01), Trello [4.2]/[4.3], status report
CR-03 | 2026-09-10 | Privacy Officer | Make multi-factor authentication (MFA) mandatory for all students, not only staff. | 3.1, 6.1 | R03, R11, ISS-05 | Small: MFA enrolment flow + help content | +2 days in Sprint 2 (absorbed by float) | +$4,200 | Reduces R03; slightly raises R11 (MFA help tickets) | Approved | 2026-09-16 | Compliance with APP 11 'reasonable steps'; low cost; uses float not critical path. | Yes — scope statement and Sprint 2 backlog | Scope statement, Trello Sprint 2 cards, training plan (6.1), risk register

## Issue_Log
Issue log
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
Issue | Date | Description | Linked risk | WBS | Impact | Owner | Corrective action | Due | Status | Days open
ISS-01 | 2026-09-22 | Trial migration 1 found 4.7% duplicate student records (≈ 1,130 of 24,000). | R01 | 4.2 | Critical task 4.2 behind plan; forecast go-live slips about 10 working days without action. | Data Engineer | CR-02 cleansing mini-sprint + contractor; Registrar decides merge rules within 2 days. | 2026-10-16 | Open — in progress | 3
ISS-02 | 2026-09-15 | LMS vendor SSO token-refresh defect breaks session after 60 minutes. | R02 | 3.5 | 3.5 at 60% vs 100% planned; uses part of its 20 days float. | Solution Architect | Vendor patch escalated via CIO (C07); workaround: shorter token lifetime. | 2026-10-02 | Open | 10
ISS-03 | 2026-08-26 | Faculty of Business requested push notifications mid-sprint. | R06 | 3.2 | Potential scope creep | Project Manager | Raised CR-01; CCB deferred to Phase 2. | 2026-09-02 | Closed
ISS-04 | 2026-09-11 | Sprint 1 accessibility scan: 2 critical colour-contrast failures. | R08 | 3.1 | WCAG metric Q04 amber | UX Designer | Fix in Sprint 2 via design-system tokens; re-scan. | 2026-10-02 | In progress | 14
ISS-05 | 2026-09-08 | Privacy Officer requires MFA for all students after PIA review. | R03 | 2.4 | Scope change | Privacy Officer | Raised CR-03; approved by CCB. | 2026-09-16 | Closed
Open issues | 3

## Traceability
Traceability matrix — one WBS ID across every tool
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
WBS | Work package | ProjectLibre ID | Trello card | Trello link | Baseline cost | Linked risks | RACI accountable | Quality metric | Critical path
1.1 | Initiation & charter | 1 | [1.1] Initiation & charter | https://trello.com/c/w6wkNBpd | 13400 | — | Sponsor | — | Yes
1.2 | Planning & baselines | 3 | [1.2] Planning & baselines | https://trello.com/c/Ftqc11da | 12960 | — | Project Manager | — | No
1.3 | Monitoring, control & CCB | 4 | [1.3] Monitoring, control & CCB | https://trello.com/c/swANm99l | 92460 | — | Project Manager | — | No
1.4 | Closure | 5 | [1.4] Closure | https://trello.com/c/JL0qAVPk | 6700 | — | Project Manager | — | Yes
2.1 | Current-state portal audit | 7 | [2.1] Current-state portal audit | https://trello.com/c/gKHXQBHA | 14800 | — | Business Analyst | — | Yes
2.2 | Requirements workshops | 8 | [2.2] Requirements workshops | https://trello.com/c/1vNe1AZp | 15600 | R06 | Business Analyst | — | Yes
2.3 | Solution & SSO architecture | 9 | [2.3] Solution & SSO architecture | https://trello.com/c/AuYqG8s9 | 18600 | R02, R12 | Solution Architect | — | Yes
2.4 | Privacy Impact Assessment | 10 | [2.4] Privacy Impact Assessment | https://trello.com/c/pjgrHDND | 10200 | R03 | Privacy Officer | — | No
2.5 | UX & accessibility prototype | 11 | [2.5] UX & accessibility prototype | https://trello.com/c/2hhm9pSY | 17700 | R08 | UX Designer | — | No
3.1 | Sprint 1 SSO & dashboard | 13 | [3.1] Sprint 1 SSO & dashboard | https://trello.com/c/sG9i1E50 | 29300 | R02, R05, R12 | Development Lead | — | No
3.2 | Sprint 2 Enrolment & timetable | 14 | [3.2] Sprint 2 Enrolment & timetable | https://trello.com/c/Oys71NKi | 29300 | R05, R06 | Development Lead | — | No
3.3 | Sprint 3 Fees & payments | 15 | [3.3] Sprint 3 Fees & payments | https://trello.com/c/krHnWWTM | 29300 | R05, R06 | Development Lead | — | No
3.4 | Sprint 4 Services & helpdesk | 16 | [3.4] Sprint 4 Services & helpdesk | https://trello.com/c/fhyGOG3V | 29300 | R05, R06 | Development Lead | — | No
3.5 | Integration APIs (SIS, LMS, Finance) | 17 | [3.5] Integration APIs (SIS, LMS, Finance) | https://trello.com/c/k2OzKmNi | 28000 | R02 | Solution Architect | — | No
3.6 | Content & notifications configuration | 18 | [3.6] Content & notifications configuration | https://trello.com/c/QfSYD0i1 | 5600 | — | Development Lead | — | No
4.1 | Data mapping & cleansing | 20 | [4.1] Data mapping & cleansing | https://trello.com/c/4bcpHzbS | 12600 | R01 | Data Engineer | — | Yes
4.2 | Migration scripts & trial migration 1 | 21 | [4.2] Migration scripts & trial migration 1 | https://trello.com/c/ab8HgR9E | 18300 | R01, R03 | Data Engineer | — | Yes
4.3 | Trial migration 2 & reconciliation | 22 | [4.3] Trial migration 2 & reconciliation | https://trello.com/c/yqJes5HD | 36600 | R01, R03 | Data Engineer | Q01 | Yes
4.4 | Final migration | 24 | [4.4] Final migration | https://trello.com/c/MziySy58 | 8900 | R03, R04 | Data Engineer | — | Yes
5.1 | System integration testing | 25 | [5.1] System integration testing | https://trello.com/c/lwu7yxdn | 34200 | — | Test Lead | — | Yes
5.2 | Security/penetration testing | 26 | [5.2] Security/penetration testing | https://trello.com/c/BEGJQGdw | 42000 | — | Test Lead | — | No
5.3 | WCAG 2.1 AA audit | 27 | [5.3] WCAG 2.1 AA audit | https://trello.com/c/nuDiYazQ | 11000 | R08 | UX Designer | Q04 | No
5.4 | Load testing (enrolment peak) | 28 | [5.4] Load testing (enrolment peak) | https://trello.com/c/QEF3XnUk | 9800 | R07 | Solution Architect | Q03 | No
5.5 | User acceptance testing | 29 | [5.5] User acceptance testing | https://trello.com/c/0OQxOzfu | 27000 | — | Test Lead | Q05 | Yes
5.6 | Regression & defect remediation | 30 | [5.6] Regression & defect remediation | https://trello.com/c/afOrVUBH | 16160 | — | Test Lead | Q06 | No
6.1 | Training & change comms | 32 | [6.1] Training & change comms | https://trello.com/c/yEbNDknS | 22400 | R09, R11 | Project Manager | — | No
6.2 | Faculty pilot | 33 | [6.2] Faculty pilot | https://trello.com/c/6RXkUi0R | 15800 | R09, R13 | Project Manager | — | Yes
6.3 | Go-live cutover | 34 | [6.3] Go-live cutover | https://trello.com/c/DK4Gh3k2 | 234600 | R04, R07, R10 | Project Manager | — | Yes
6.4 | Hypercare | 36 | [6.4] Hypercare | https://trello.com/c/8S47PE06 | 47600 | R11 | Project Manager | Q02, Q07 | Yes
6.5 | Legacy portal decommissioning | 37 | [6.5] Legacy portal decommissioning | https://trello.com/c/66UQ2c1G | 10000 | — | Project Manager | — | Yes
| Work packages traced | 30

## Closure
Closure checklist, benefits realisation and lessons learned
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
# | Closure item | Owner | Status
1 | All deliverables accepted against acceptance criteria | Project Manager | Not started
2 | Registrar sign-off on final migration reconciliation | Academic Registrar | Not started
3 | UAT, security and WCAG reports archived | Test Lead | Not started
4 | Legacy portals decommissioned and data archived per retention schedule | Solution Architect | Not started
5 | Privacy Officer confirms non-production data destroyed | Privacy Officer | Not started
6 | Vendor contracts closed; contractor access revoked | Finance Office | Not started
7 | Final cost reconciliation vs budget; unused reserves returned | Project Manager | Not started
8 | Handover to BAU support (runbooks, knowledge base, SLAs) | Development Lead | Not started
9 | Benefits realisation plan handed to sponsor | Sponsor | Not started
10 | Lessons learned workshop held and register published | Project Manager | In progress (captured each sprint)
11 | Trello board archived; ProjectLibre final actuals saved | Project Manager | Not started
12 | Team released and recognised | Project Manager | Not started
13 | Closure report approved by steering committee (M7) | Sponsor | Not started
| Items complete |  | 0 of 13
Benefits realisation plan
# | Benefit / KPI | Baseline → Target | Measure date / Owner
1 | Fewer helpdesk tickets — KPI: Portal-related tickets per month | 4,200 → ≤ 2,940 (−30%) | 30/04/2027 · IT Service Desk Manager
2 | Single login — KPI: % of students using SSO + MFA | 0% → ≥ 95% | 31/03/2027 · CIO
3 | Legacy cost savings — KPI: Annual licence + support cost of legacy portals | $140k/yr → $0 after decommissioning | 30/06/2027 · Finance Office
4 | Data quality — KPI: Duplicate student records | 4.7% (trial 1) → < 0.5% | 31/03/2027 · Academic Registrar
5 | Student experience — KPI: Portal satisfaction (survey, 1–5) | 2.9 → ≥ 4.0 | 31/05/2027 · DVC (Education)
Lessons learned (what happened / impact / recommendation)
ID | What happened | Impact | Recommendation
L1 | Data profiling in 2.1 sampled only 5% of records. | Duplicates found late (ISS-01), on the critical path. | Profile 100% of keys before mapping; make data quality a gate at M2.
L2 | LMS SSO proof of concept ran inside Sprint 1. | Token defect (ISS-02) surfaced early enough to use float. | Keep technical spikes before dependent sprints.
L3 | Faculty feature requests arrived informally. | Risk of scope creep (CR-01). | Publish the CCB process in the charter and at every faculty briefing.
L4 | Accessibility scans ran from Sprint 1. | Contrast failures fixed cheaply (ISS-04). | Automate WCAG scans in the build pipeline.
L5 | EVM reported weekly from week 4. | SPI drop visible within a week of ISS-01. | Keep weekly EVM with RAG thresholds agreed by the sponsor.
L6 | Contingency reserve was sized from risk EMVs. | CR-02 was funded without new approval. | Link each reserve dollar to a named risk.
L7 | Privacy Officer joined the CCB. | MFA decision (CR-03) made in one week. | Include compliance roles on the CCB from initiation.

## Schedule_WBS
Schedule & WBS work packages (mirrors A2_GroupXX_ProjectLibre.pod)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
WBS | Branch | Task | Duration (d) | PL ID | Baseline start | Baseline finish | Forecast finish | Total float (d) | Forecast float (d) | Critical | Labour cost | Fixed cost | Baseline cost (BAC) | Planned % at status | % complete | PV | EV | AC (actual) | Owner (RACI A)
1.1 | 1 | Initiation & charter | 10 | 1 | 2026-07-06 | 2026-07-17 | 2026-07-17 | 0 | 0 | Yes | 13400 | 0 | 13400 | 100% | 100% | 13400 | 13400 | 13400 | Sponsor
M1 | 1 | Charter approved | 0 | 2 | 2026-07-20 | 2026-07-17 | 2026-07-17 | 0 | 0 | Yes | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | Project Manager
1.2 | 1 | Planning & baselines | 8 | 3 | 2026-07-20 | 2026-07-29 | 2026-07-29 | 2 | 2 | No | 12960 | 0 | 12960 | 100% | 100% | 12960 | 12960 | 12960 | Project Manager
1.3 | 1 | Monitoring, control & CCB | 138 | 4 | 2026-07-30 | 2027-02-19 | 2027-02-19 | 9 | 19 | No | 92460 | 0 | 92460 | 30.43% | 30.43% | 28140 | 28140 | 28140 | Project Manager
1.4 | 1 | Closure | 5 | 5 | 2027-03-05 | 2027-03-11 | 2027-03-25 | 0 | 0 | Yes | 6700 | 0 | 6700 | 0% | 0% | 0 | 0 | 0 | Project Manager
M7 | 1 | Project closed | 0 | 6 | 2027-03-12 | 2027-03-11 | 2027-03-25 | 0 | 0 | Yes | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
2.1 | 2 | Current-state portal audit | 10 | 7 | 2026-07-20 | 2026-07-31 | 2026-07-31 | 0 | 0 | Yes | 14800 | 0 | 14800 | 100% | 100% | 14800 | 14800 | 14800 | Business Analyst
2.2 | 2 | Requirements workshops | 10 | 8 | 2026-08-03 | 2026-08-14 | 2026-08-14 | 0 | 0 | Yes | 15600 | 0 | 15600 | 100% | 100% | 15600 | 15600 | 15600 | Business Analyst
2.3 | 2 | Solution & SSO architecture | 10 | 9 | 2026-08-17 | 2026-08-28 | 2026-08-28 | 0 | 0 | Yes | 18600 | 0 | 18600 | 100% | 100% | 18600 | 18600 | 22320 | Solution Architect
2.4 | 2 | Privacy Impact Assessment | 10 | 10 | 2026-08-24 | 2026-09-04 | 2026-09-04 | 10 | 20 | No | 10200 | 0 | 10200 | 100% | 100% | 10200 | 10200 | 10200 | Privacy Officer
2.5 | 2 | UX & accessibility prototype | 15 | 11 | 2026-08-17 | 2026-09-04 | 2026-09-04 | 10 | 20 | No | 17700 | 0 | 17700 | 100% | 100% | 17700 | 17700 | 17700 | UX Designer
M2 | 2 | Design sign-off | 0 | 12 | 2026-09-07 | 2026-09-04 | 2026-09-04 | 10 | 20 | No | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | Project Manager
3.1 | 3 | Sprint 1 SSO & dashboard | 10 | 13 | 2026-08-31 | 2026-09-11 | 2026-09-11 | 5 | 15 | No | 29300 | 0 | 29300 | 100% | 100% | 29300 | 29300 | 29300 | Development Lead
3.2 | 3 | Sprint 2 Enrolment & timetable | 10 | 14 | 2026-09-14 | 2026-09-25 | 2026-09-25 | 5 | 15 | No | 29300 | 0 | 29300 | 100% | 80% | 29300 | 23440 | 23440 | Development Lead
3.3 | 3 | Sprint 3 Fees & payments | 10 | 15 | 2026-09-28 | 2026-10-12 | 2026-10-12 | 5 | 15 | No | 29300 | 0 | 29300 | 0% | 0% | 0 | 0 | 0 | Development Lead
3.4 | 3 | Sprint 4 Services & helpdesk | 10 | 16 | 2026-10-13 | 2026-10-26 | 2026-10-26 | 5 | 15 | No | 29300 | 0 | 29300 | 0% | 0% | 0 | 0 | 0 | Development Lead
3.5 | 3 | Integration APIs (SIS, LMS, Finance) | 20 | 17 | 2026-08-31 | 2026-09-25 | 2026-09-25 | 5 | 15 | No | 28000 | 0 | 28000 | 100% | 70% | 28000 | 19600 | 19600 | Solution Architect
3.6 | 3 | Content & notifications configuration | 10 | 18 | 2026-09-28 | 2026-10-12 | 2026-10-12 | 15 | 25 | No | 5600 | 0 | 5600 | 0% | 0% | 0 | 0 | 0 | Development Lead
M3 | 3 | Build complete | 0 | 19 | 2026-10-27 | 2026-10-26 | 2026-10-26 | 5 | 15 | No | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
4.1 | 4 | Data mapping & cleansing | 10 | 20 | 2026-08-31 | 2026-09-11 | 2026-09-11 | 0 | 0 | Yes | 12600 | 0 | 12600 | 100% | 100% | 12600 | 12600 | 15120 | Data Engineer
4.2 | 4 | Migration scripts & trial migration 1 | 15 | 21 | 2026-09-14 | 2026-10-02 | 2026-10-19 | 0 | 0 | Yes | 18300 | 0 | 18300 | 66.67% | 30% | 12200 | 5490 | 9150 | Data Engineer
4.3 | 4 | Trial migration 2 & reconciliation | 20 | 22 | 2026-10-06 | 2026-11-02 | 2026-11-16 | 0 | 0 | Yes | 36600 | 0 | 36600 | 0% | 0% | 0 | 0 | 0 | Data Engineer
M4 | 4 | Trial migration passed | 0 | 23 | 2026-11-03 | 2026-11-02 | 2026-11-16 | 0 | 0 | Yes | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
4.4 | 4 | Final migration | 5 | 24 | 2027-01-07 | 2027-01-13 | 2027-01-28 | 0 | 0 | Yes | 8900 | 0 | 8900 | 0% | 0% | 0 | 0 | 0 | Data Engineer
5.1 | 5 | System integration testing | 15 | 25 | 2026-11-03 | 2026-11-23 | 2026-12-07 | 0 | 0 | Yes | 34200 | 0 | 34200 | 0% | 0% | 0 | 0 | 0 | Test Lead
5.2 | 5 | Security/penetration testing | 10 | 26 | 2026-10-27 | 2026-11-09 | 2026-11-09 | 25 | 35 | No | 17000 | 25000 | 42000 | 0% | 0% | 0 | 0 | 0 | Test Lead
5.3 | 5 | WCAG 2.1 AA audit | 10 | 27 | 2026-10-20 | 2026-11-02 | 2026-11-02 | 30 | 40 | No | 11000 | 0 | 11000 | 0% | 0% | 0 | 0 | 0 | UX Designer
5.4 | 5 | Load testing (enrolment peak) | 10 | 28 | 2026-11-10 | 2026-11-23 | 2026-12-07 | 15 | 15 | No | 9800 | 0 | 9800 | 0% | 0% | 0 | 0 | 0 | Solution Architect
5.5 | 5 | User acceptance testing | 15 | 29 | 2026-11-24 | 2026-12-14 | 2027-01-06 | 0 | 0 | Yes | 27000 | 0 | 27000 | 0% | 0% | 0 | 0 | 0 | Test Lead
5.6 | 5 | Regression & defect remediation | 8 | 30 | 2026-12-01 | 2026-12-10 | 2027-01-04 | 2 | 2 | No | 16160 | 0 | 16160 | 0% | 0% | 0 | 0 | 0 | Test Lead
M5 | 5 | UAT sign-off | 0 | 31 | 2026-12-15 | 2026-12-14 | 2027-01-06 | 0 | 0 | Yes | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.1 | 6 | Training & change comms | 20 | 32 | 2026-10-27 | 2026-11-23 | 2026-11-23 | 30 | 40 | No | 14400 | 8000 | 22400 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.2 | 6 | Faculty pilot | 10 | 33 | 2026-12-15 | 2027-01-06 | 2027-01-20 | 0 | 0 | Yes | 15800 | 0 | 15800 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.3 | 6 | Go-live cutover | 5 | 34 | 2027-01-14 | 2027-01-20 | 2027-02-04 | 0 | 0 | Yes | 18600 | 216000 | 234600 | 0% | 0% | 0 | 0 | 0 | Project Manager
M6 | 6 | Go-live | 0 | 35 | 2027-01-21 | 2027-01-20 | 2027-02-04 | 0 | 0 | Yes | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.4 | 6 | Hypercare | 20 | 36 | 2027-01-21 | 2027-02-18 | 2027-03-04 | 0 | 0 | Yes | 47600 | 0 | 47600 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.5 | 6 | Legacy portal decommissioning | 10 | 37 | 2027-02-19 | 2027-03-04 | 2027-03-18 | 0 | 0 | Yes | 10000 | 0 | 10000 | 0% | 0% | 0 | 0 | 0 | Project Manager
|  | Totals (BAC / PV / EV / AC) | [8 empty] | 651180 | 249000 | 900180 |  |  | 242800 | 221830 | 231730
Amber rows = behind plan at the status date (% complete < planned %). PV/EV/AC equal ProjectLibre BCWS/BCWP/ACWP per task.

## Assignments
Resource assignments (from the ProjectLibre plan)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
WBS | Role | Units | Baseline duration (d) | Hours | Rate | Labour cost
1.1 | Project Manager | 100% | 10 | 80 | 120 | 9600
1.1 | Business Analyst | 50% | 10 | 40 | 95 | 3800
1.2 | Project Manager | 100% | 8 | 64 | 120 | 7680
1.2 | Business Analyst | 50% | 8 | 32 | 95 | 3040
1.2 | Solution Architect | 25% | 8 | 16 | 140 | 2240
1.3 | Project Manager | 50% | 138 | 552 | 120 | 66240
1.3 | Business Analyst | 25% | 138 | 276 | 95 | 26220
1.4 | Project Manager | 100% | 5 | 40 | 120 | 4800
1.4 | Business Analyst | 50% | 5 | 20 | 95 | 1900
2.1 | Business Analyst | 100% | 10 | 80 | 95 | 7600
2.1 | Data Engineer | 50% | 10 | 40 | 110 | 4400
2.1 | Solution Architect | 25% | 10 | 20 | 140 | 2800
2.2 | Business Analyst | 100% | 10 | 80 | 95 | 7600
2.2 | UX Designer | 50% | 10 | 40 | 95 | 3800
2.2 | Project Manager | 25% | 10 | 20 | 120 | 2400
2.2 | Change & Training Lead | 25% | 10 | 20 | 90 | 1800
2.3 | Solution Architect | 100% | 10 | 80 | 140 | 11200
2.3 | Security Consultant | 25% | 10 | 20 | 160 | 3200
2.3 | Developer | 50% | 10 | 40 | 105 | 4200
2.4 | Business Analyst | 50% | 10 | 40 | 95 | 3800
2.4 | Security Consultant | 50% | 10 | 40 | 160 | 6400
2.5 | UX Designer | 100% | 15 | 120 | 95 | 11400
2.5 | Developer | 50% | 15 | 60 | 105 | 6300
3.1 | Developer | 200% | 10 | 160 | 105 | 16800
3.1 | Tester | 100% | 10 | 80 | 85 | 6800
3.1 | UX Designer | 50% | 10 | 40 | 95 | 3800
3.1 | Business Analyst | 25% | 10 | 20 | 95 | 1900
3.2 | Developer | 200% | 10 | 160 | 105 | 16800
3.2 | Tester | 100% | 10 | 80 | 85 | 6800
3.2 | UX Designer | 50% | 10 | 40 | 95 | 3800
3.2 | Business Analyst | 25% | 10 | 20 | 95 | 1900
3.3 | Developer | 200% | 10 | 160 | 105 | 16800
3.3 | Tester | 100% | 10 | 80 | 85 | 6800
3.3 | UX Designer | 50% | 10 | 40 | 95 | 3800
3.3 | Business Analyst | 25% | 10 | 20 | 95 | 1900
3.4 | Developer | 200% | 10 | 160 | 105 | 16800
3.4 | Tester | 100% | 10 | 80 | 85 | 6800
3.4 | UX Designer | 50% | 10 | 40 | 95 | 3800
3.4 | Business Analyst | 25% | 10 | 20 | 95 | 1900
3.5 | Developer | 100% | 20 | 160 | 105 | 16800
3.5 | Solution Architect | 50% | 20 | 80 | 140 | 11200
3.6 | Business Analyst | 50% | 10 | 40 | 95 | 3800
3.6 | Change & Training Lead | 25% | 10 | 20 | 90 | 1800
4.1 | Data Engineer | 100% | 10 | 80 | 110 | 8800
4.1 | Business Analyst | 50% | 10 | 40 | 95 | 3800
4.2 | Data Engineer | 100% | 15 | 120 | 110 | 13200
4.2 | Tester | 50% | 15 | 60 | 85 | 5100
4.3 | Data Engineer | 100% | 20 | 160 | 110 | 17600
4.3 | Tester | 50% | 20 | 80 | 85 | 6800
4.3 | Business Analyst | 25% | 20 | 40 | 95 | 3800
4.3 | Developer | 50% | 20 | 80 | 105 | 8400
4.4 | Data Engineer | 100% | 5 | 40 | 110 | 4400
4.4 | Solution Architect | 50% | 5 | 20 | 140 | 2800
4.4 | Tester | 50% | 5 | 20 | 85 | 1700
5.1 | Tester | 150% | 15 | 180 | 85 | 15300
5.1 | Developer | 150% | 15 | 180 | 105 | 18900
5.2 | Security Consultant | 100% | 10 | 80 | 160 | 12800
5.2 | Developer | 50% | 10 | 40 | 105 | 4200
5.3 | UX Designer | 100% | 10 | 80 | 95 | 7600
5.3 | Tester | 50% | 10 | 40 | 85 | 3400
5.4 | Solution Architect | 50% | 10 | 40 | 140 | 5600
5.4 | Developer | 50% | 10 | 40 | 105 | 4200
5.5 | Tester | 100% | 15 | 120 | 85 | 10200
5.5 | Business Analyst | 100% | 15 | 120 | 95 | 11400
5.5 | Change & Training Lead | 50% | 15 | 60 | 90 | 5400
5.6 | Developer | 200% | 8 | 128 | 105 | 13440
5.6 | Tester | 50% | 8 | 32 | 85 | 2720
6.1 | Change & Training Lead | 100% | 20 | 160 | 90 | 14400
6.2 | Change & Training Lead | 50% | 10 | 40 | 90 | 3600
6.2 | Business Analyst | 50% | 10 | 40 | 95 | 3800
6.2 | Developer | 100% | 10 | 80 | 105 | 8400
6.3 | Solution Architect | 100% | 5 | 40 | 140 | 5600
6.3 | Developer | 200% | 5 | 80 | 105 | 8400
6.3 | Data Engineer | 50% | 5 | 20 | 110 | 2200
6.3 | Project Manager | 50% | 5 | 20 | 120 | 2400
6.4 | Developer | 200% | 20 | 320 | 105 | 33600
6.4 | Change & Training Lead | 50% | 20 | 80 | 90 | 7200
6.4 | Tester | 50% | 20 | 80 | 85 | 6800
6.5 | Solution Architect | 50% | 10 | 40 | 140 | 5600
6.5 | Data Engineer | 50% | 10 | 40 | 110 | 4400

## Resources
Resources and rates (AUD)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
Role | Count (FTE) | Rate per hour | Type | Baseline hours | Baseline labour cost
Project Manager | 1 | 120 | Work | 776 | 93120
Business Analyst | 1 | 95 | Work | 928 | 88160
Solution Architect | 1 | 140 | Work | 336 | 47040
Developer | 3 | 105 | Work | 1848 | 194040
Data Engineer | 1 | 110 | Work | 500 | 55000
Tester | 2 | 85 | Work | 932 | 79220
UX Designer | 1 | 95 | Work | 400 | 38000
Change & Training Lead | 1 | 90 | Work | 380 | 34200
Security Consultant | 1 | 160 | Work (contract) | 140 | 22400
Total |  |  |  | 6240 | 651180

## Lookups
Lookups & scoring scales
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml
Likelihood | Label | Band | Probability |  | Strategy | Status | CCB decision | RAG | RACI | Holidays (NSW + SCU shutdown)
1 | Rare | < 10% | 5% |  | Avoid | Open | Approved | Green | R | 2026-10-05 | Labour Day (NSW)
2 | Unlikely | 10–30% | 15% |  | Mitigate | In progress | Deferred | Amber | A | 2026-12-24 | University shutdown
3 | Possible | 30–50% | 40% |  | Transfer | Closed | Rejected | Red | C | 2026-12-25 | Christmas Day
4 | Likely | 50–80% | 65% |  | Accept | Not started | Pending | Grey | I | 2026-12-28 | Boxing Day (observed)
5 | Almost certain | > 80% | 90% |  | Exploit | Done |  |  |  | 2026-12-29 | University shutdown
[5 empty] | Enhance |  |  |  |  | 2026-12-30 | University shutdown
Impact | Label | Cost | Schedule | Other | Share |  |  |  |  | 2026-12-31 | University shutdown
1 | Insignificant | < $5k | < 2 days | No external visibility | [5 empty] | 2027-01-01 | New Year's Day
2 | Minor | $5k–15k | 2–5 days | Internal complaints | [5 empty] | 2027-01-26 | Australia Day
3 | Moderate | $15k–40k | 1–2 weeks | Student complaints; SRC attention | [5 empty] | 2027-03-26 | Good Friday
4 | Major | $40k–100k | 2–4 weeks; milestone missed | Media/regulator enquiry | [5 empty] | 2027-03-29 | Easter Monday
5 | Severe | > $100k | > 4 weeks; go-live deadline missed | Notifiable data breach; TEQSA action
Rating | Min score | Max score | Colour
Low | 1 | 4 | green
Medium | 5 | 9 | yellow
High | 10 | 16 | orange
Extreme | 20 | 25 | red